# Examples of how Actions can be Documented

| Public Relations |
| --- |
| SPECIFIC ACTION | EXPECTED DURATION | PROCESS | PERSON/S RESPONSIBLE | EVALUATION CRITERIA |
| Strategy developed and documented | 3 months | Facilitator will be engaged to work with full time staff team | Full staff team Action Co-Ordinator P. Durnin | PR strategy is documented in consultation with staff team The strategy identifies the audience for various PR work The strategy contains an annual plan for engaging in PR Training is identified |
| Training provided for relevant members of staff | 3 months | Staff take part in regional training | P. Durnin to organise training | Responsibility for Public Relations is assigned Training is organised regionally Relevant staff members attend training as appropriate |
| Implement PR Strategy | On-going following implementation of above actions | Actions set out in the PR strategy are implemented | Staff members assigned with responsibility for PR | To be established on completion of PR strategy |

# Examples of how Actions can be Documented

| Recruitment of Learners and Admission |
| --- |
| SPECIFIC ACTION | EXPECTED DURATION | PROCESS | PERSON/S RESPONSIBLE | EVALUATION CRITERIA |
| Develop an Admission Policy and document admission procedures | 5 weeks | Develop policy across all centres within the VEC. Engage a facilitator to work with a team of people including reps. From each centre | Action Co-Ordinator: Peter Delaney Peter to co-ordinate process across all 4 centres | Facilitator is engaged Policy is developed Policy meets the approval of the VEC and the staff in each centre Monitoring arrangements are agreed (as appropriate to each centre) |
| Review current advertising/recruitment arrangements and develop more appropriate | 8 weeks | Staff member reviews and documents current arrangements | Lisa Duffy | The current arrangements are documented A proposal for developing a more appropriate advertising/recruitment is planned and agreed with the centre Co-Ordinator/Director The new system is tried out for September recruitment phase |
| Meet with schools in order to improve referral links | 4 weeks | Staff members arrange meetings with relevant school personnel with a view to developing improved arrangements | Karl Lunny Marie Walsh | Relevant school personnel are identified Meetings are arranged More appropriate referral procedures are established Necessary documentation/records are maintained |

# Examples of how Actions can be Documented

| Literacy and Numeracy |
| --- |
| SPECIFIC ACTION | EXPECTED DURATION | PROCESS | PERSON/S RESPONSIBLE | EVALUATION CRITERIA |
| A Literacy Plan will be developed and implemented | 9 months | Centre Co-Ordinator/Director meet with staff as required to develop plan Representative from NALA to meet with staff | Action Co-Ordinator: Paddy Blake, together with full staff team | Representative from NALA gives presentation to staff team Relevant reference material is collated Research is carried out The Literacy Plan is developed Monitoring arrangements are agreed The plan is implemented from February 2006 |
| Specialised training is the area of Literacy is provided to relevant staff | 6 months | Following the completion of the Literacy Plan, relevant staff are identified and training is organised | Paddy Blake | Relevant staff are identified Appropriate training is identified Funding for training is allocated Staff participate in training programme |